7

PROJECT IMPLEMENTATION FRAMEWORK & TECHNICAL ASSISTANCE

Town Investment Plan is an operational action plan to achieve a set of development objectives within a specific period, keeping in view the existing financial profile and capacity to raise revenue from various known alternatives. It provides an estimate of the level of investment needed for the identified development projects. This Town Investment Plan has identified gaps in service delivery and institutional management, ascertained by analysis and stakeholder feedback. The proposed interventions for the Town Panchayat are in the form of reforms, action plans and strategies to achieve the same.

The following sections detail out the strategies and implementation framework for the proposed reforms and interventions in the areas of Revenue enhancement, Privatization, Computerization initiatives, Energy efficiency and Infrastructure service delivery.

“Reforms and change are critical elements in development process; they become more significant in urban development in the context of growth of towns and consequent pressure on infrastructure and services, growth of poverty, etc. This is compounded by institutional constraints like fragmented structures, functional overlaps and outdated processes and procedures. There has also been a paradigm shift in governance from the traditional top-down model. As a result governance reforms have become imperative for efficient delivery of services, provision and maintenance of infrastructure and to provide efficient and responsive governance to the people.

Recognizing the significance of reforms to provide efficient and effective governance, the State Govt. has initiated and implemented several urban sector reforms during the last few years.”

The urban reforms for Town Panchayats are at two levels namely; Reforms at the ULB/Parastatal level and Reforms at State level. The various reforms are as follows:

7.1.1.	Reforms at State Level

- Implementation of decentralization measures as envisaged in 74th Constitution Amendment Act

- *Repeal of Urban Land Ceiling and Regulation Act

- Reform of Rent Control Laws balancing the interests of landlords and tenants

- Rationalization of Stamp Duty to bring it down to no more than 5% within next seven years

- Enactment of Public Disclosure Law to ensure preparation of medium-term fiscal plan of ULBs/ Parastatals and release of quarterly performance information to all stakeholders

- Enactment of Community Participation Law to institutionalize citizen participation and introducing the concept of Area Sabha in urban areas

- Assigning or associating elected ULBs with “City Planning Function”. Over a period of seven years, transferring all special agencies that deliver civic services in urban areas to ULBs and creating accountability platforms for all urban civic service providers in transition

Optional Reforms (State and ULB/Parastatal level)

- Revision of bye-laws to streamline the approval process for construction of buildings, development of sites etc.

- Simplification of legal and procedural frameworks for conversion of agricultural land for non-agricultural purposes.

- Introduction of Property Title Certification System in ULBs.

- Earmarking at least 20-25% of developed land in all housing projects (both Public and Private Agencies) for EWS/LIG category with a system of cross subsidization.

- Introduction of computerized process of registration of land and property.

- Revision of bye-laws to make rain water harvesting mandatory in all buildings and adoption of water conservation measures.

- Bye-laws for reuse of recycled water.

- Administrative reforms i.e. reduction in establishment by bringing out voluntary retirement schemes, non-filling up of posts falling vacant due to retirement etc., and achieving specified milestones in this regard.

- Structural reforms

- Encouraging Public Private Partnership .

7.1.2.	Reforms at Urban Local Body / Parastatal

- Adoption of modern, accrual-based double entry system of accounting in Urban Local Bodies / Parastatals

- Introduction of system of e-governance using IT applications like, GIS and MIS for various services provided by ULBs / Parastatals.

- Reform of property tax with GIS, so that it becomes major source of revenue for Urban Local Bodies (ULBs) and arrangements for its effective implementation so that collection efficiency reaches at least 85% within next seven years.

- Levy of reasonable user charges by ULBs/ Parastatals with the objective that full cost of operation and maintenance or recurring cost is collected within next seven years.

- Internal earmarking within local body, budgets for basic services to the urban poor.

- Provision of basic services to urban poor including security of tenure at affordable prices, improved housing, water supply, sanitation and ensuing delivery of other already existing universal services of the Government for education, health and social security.

(Source: Proactive disclosure of Information, Commissionerate of Town Panchayats, Chennai)

7.2	PROPOSED REFORMS AT STATE LEVEL

1.	Reforms in Taxation *

- Property mapping exercise

- Periodic revision of property tax & profession tax

- Early bird Discounts

- Penalty for defaulters

* - Detailed out in section 7.3.1.1.

- ‘Capital Value-based property tax system’, instead of the present ‘Annual Rental Value based property tax system’

  - The system of property taxation followed in the urban local bodies is a rent-based rateable valuation system where the annual value or the annual rental value ( ARV) of the property shall be deemed to be “the gross annual rent at which the land or buildings might, at the time of assessment.” An alternative provision for assessment of properties on capital value basis can be initiated in the urban local bodies. In this the annual value is arrived at on the basis of estimated market value of land and cost of construction at the time of construction or acquisition.

2.	Public Private Participation

- Need for a policy frame work

Although the GoTN has not initiated the PPP policy, a clear policy to define the use of PPPs, the basis for their use, provides political commitment and support for the program. This could be vital particularly in the early years of PPP ventures. The main points that may be addressed in the PPP policy are as listed below:

- The Policy must stress on PPPs as a provider of better services to the urban masses and not a tool to attract private investors to supplement Government deficits.

- The policy can provide clarity on other aspects, such as the approach towards risk transfer, procurement, financing, and the need for transparency.

- It should also encourage the discussion of key issues among different stakeholders, for a better understanding of the main characteristics of PPPs, their advantages, and their drawbacks. This would ensure a win-win situation for both public and private sectors.

- Need for a legal framework

At the National level, PPP law has been implemented in Gujarat, Andhra Pradesh and Punjab. In Tamil Nadu, sector specific amendments have been used to facilitate PPPs as in the case of Karur toll bridge wherein the ‘TN State Toll Act’ was amended to facilitate ULB to enter into BoT contract.

However, a PPP law would be beneficial in consolidating relevant legal provisions into one, and legislating the process of procurement, development and regulation of PPP projects, dispute settlements, which can be better enforced by law.

This is especially important at the ULB/ Regional levels where the techno-legal capabilities might not be as good as at the State/ Central level. A model law at the Central level or the existing laws in Gujarat, Andhra Pradesh and Punjab would serve as base for GoTN.

- Need for strengthening the institutional framework.

The PPP cell at the State level is a GoTN venture. To improve the turnaround in the number of projects, expertise at TNUIFSL may be roped in for providing consultancy services for PPP projects. A Regional PPP cell constituting authorities from GoTN, TNUIFSL and Financial Institutions may be constituted, the expenses on which can be borne by project basis. Alternatively, Private consultants could be appointed for project structuring and PMC for specialised projects as in the case of TNHB JV projects.

A single window approach system at the State or Regional levels through agencies such as TNUIFSL for technical and contractual guidance for the ULBs aspiring to execute the projects identified would also address the need for techno-legal guidance for projects. After the first few projects, Regional authorities and the executive heads of the ULBs (champions) would have gained considerable knowledge which could be disseminated to the others. Constant transfer of administrative ‘champions’ also weaken reform initiatives.

Empanelling private investors and consultants for each sector, based on past experience, size of the projects and PPP modality would also facilitate policy makers to identify availability or gaps in the various sectors of urban infrastructure.

- Information dissemination

At the central and bureaucratic levels, PPP workshops and seminars have been conducted by the World Bank, ADB and the Department of Economic affairs. But there has been little trickle down of information to the authorities in need of information such as ULB officials, authorities of line agencies etc.

The first step in information dissemination could be setting up a publicly-accessible database on PPPs at the state, regional and local levels to contain information on

  - Contract design for various sectors

  - Procedures for identifying, procuring and managing PPPs

  - Transfer of risks

  - Various PPP models

  - Analysis of successes and failures

  - Case studies of success models with regular performance updates

  - Empanelled list of private operators under various sectors and models at the National and State level.

  - Regular updates form resource centres and personnel , on line paper publications,

  - Information on successful contractor, progress of awarded projects and mile stones achieved.

  - Sector toolkits can be developed once sufficient sector experience has been achieved.

- Need for Political consensus

Stable political consensus at state and Ulb levels from the EOI stage till the Financial Closure of the project is one of the main factors that would determine the success of PPP projects. In the case Tamil Nadu, the success of every PPP project will account for creating conducive environment for prospective private investors.

- Addressing size based constraints

Although projects of considerable size only are viable under PPP, clustering of similar projects in the region would overcome this challenge faced by many small and medium Towns in Tamil Nadu. A good example would be the WSPF under which WS / UGSS projects for 14 Municipalities have been clubbed to build a common resource base.

- Strategies for identifying PPP projects.

Step-1

From the compiled list of priority projects across all ULBs, investigate each project sector wise and size wise for viability under PPP option.

Step-2

Analyze and compare against EPC projects for the benefits in terms of time, cost, technology options and PPP model applicable. The more advantageous option for the particular sector / project to be finalised.

Step -3

The projects selected under PPP ventures to be listed down and cross referenced with the availability of private investors in a particular sector. Unbundling of services would facilitate bridging any gaps in the availability of private players and also would facilitate local firms in bidding for the project, thus increasing competition.

3.	Infrastructure Reforms

Water supply

- As regards water supply projects, the consultant proposes using available local sources (surface water) in lieu of capital intensive projects from far off sources. The enforcement of RWH in all buildings is a commendable initiative, which has proven successful in improving the quality and quantity of ground water table according to a recent study. Rejuvenation and protection of water bodies and recycling, reuse of water is also a major issue to be addressed in this regard. Participation of SHGS, voluntary organizations, resident welfare associations need to be sought.

Sewerage system

- Highly engineered and mechanized conventional sewage treatment requires large Capital Investment; demand high maintenance costs are not feasible for the developing countries like India. Capital intensive and highly technological waste disposal solutions, utilizing indiscriminate collection and large-scale disposal, do not consider the value of recovering organic waste resources and do not promote recycling. The land required for the disposal of treated wastewater in the conventional treatment systems is not readily available in and around urban area. Alternative treatment systems like DWATS, EcoSan methods could be used.

- Government of Tamil Nadu must enforce recycle of water in residential complexes, industrial public and semi-public and institutional buildings. The model adapted for RWH may be followed to expedite ‘Water Recycle Initiative’. The support of NGOs, CBOs, and educational institutions may be sought for the purpose of information dissemination.

7.3	PROPOSED REFORMS AT ULB LEVEL

The Proposed interventions are broadly categorized under the heads of:

- Reforms in Resource Mobilisation

- Privatisation Initiatives

- Energy & resource efficiency

- Computerization and E-governance

- Accounts and Auditing

- Municipal service delivery

7.3.1	Reforms in Resource Mobilisation

In an environment in which business activity is booming and urban infrastructure threatens to become a constraint to growth, the municipalities are faced with an unprecedented need to find substantial resources for development, and an unprecedented opportunity to raise the same. The various options for enhancement of Municipal revenue based is discussed below:

- Improving revenue from own sources

- Improving revenue from user charges

- Formation of new sustainable revenue bases

7.3.1.1.	Strategies for Improving Revenue from Own Sources

  - Property Mapping Exercise

Onetime assessment of all unassessed and under assessed properties. The project could be taken up as a door –to –door survey of all existing properties, with details on

- Size & built up area of the property

- Present use - residential, commercial, industrial or vacant.

Street naming and property numbering already undertaken by Govt. of Tamil Nadu needs to be linked to this to streamline the study. Property mapping would form a database for GIS projects (Land use and Utility Mapping), which is a long term project and in the rationalization of tax structure.

- Periodic revision of property tax & profession tax – Need for political and public consensus. Revision of property tax has fallen due in 2003 and the actual increase was carried out in 2008 at rates varying from 20-25%. This is due to oppositions from non-willingness of elected representatives to collect, public oppositions etc.

- Periodic increment from  rental and fee based items

All rental and fee based income such as commercial complexes, Building license , D&O license, WS / UGSS tariff and deposits , leased properties and buildings, to be revised on periodical basis.

  - Early Bird Offers

Most of the collections take place during the last quarter of the year. This results in poor collection efficiency, wherein the ULB ends up collecting much less taxes than the tax demand raised. The option of providing rebates upto 10% for ‘early birds’ paying the tax during the 1st and 2nd quarter could be explored. This would ensure timely spending on capital and operating expenditure and efficient tax management systems.

  - Levy of penalty on unauthorised construction until regularization and approval.

d.	Expanding Profession tax base.

Identifying and including omitted Profession tax assessees. This project is to be linked to the property mapping exercise. An improvement of 20-30% on the existing tax base could be expected. The participation of the SHGs, (youth and women) could be utilized for the purpose.

## Table 7.1 Road Map - Improving revenue from own sources

| S.N | Reforms |  | Year of Implementation |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| 1 | Property tax Reform |  |  |  |  |  |  |
|  | i | Property Mapping |  |  |  |  |  |
|  | ii | Rebates on Property tax |  |  |  |  |  |
|  | iii | Regular and periodic increment of property tax |  |  |  |  |  |
| 2 | Reassessing profession tax assesses |  |  |  |  |  |  |
| 3 | Levy of penalty on unauthorized construction. |  |  |  |  |  |  |
| 4 | Reassessment of omitted Professional tax assessees |  |  |  |  |  |  |

## 7.3.1.2	Strategies for Improving Revenue from User Charges

- Water supply and Sewerage

- Fixing of bulk water meter at apartment complexes, commercial, industrial, hospitals, marriage halls and educational institutions.

- Approval of the council for the proposed tariff and deposit structure to enhance the public contribution and meet the entire O&M cost.

- Increase in the House Service Connections to at least 85% of the total assessments. This backed by higher collection efficiency and enforced leakage losses (less than 15%) would further improve service delivery.

- Levy Reasonable User Charges to recover full O&M Cost of water supply and UGSS.

- Implementation of graded tariff structure (UGSS) for domestic and non-domestic connections. This needs to be linked to property mapping project and type of assessment to be ensured.

- Mandatory mobilization of deposits for Capital intensive WS or UGSS projects during pre-construction stage of the project.

- Regular and periodic increase in tariff and deposit structure every 5 years.

- Solid Waste Management

- Approval of the Municipal council for the proposed Solid waste conservancy charges for domestic assessments, commercial and industrial establishments.

- For implementing collection of conservancy fee for Solid waste Management .The proposed tariff structure is given below:

- Domestic	- Rs.25 per assessment

- Commercial 	- Rs.50 per assessment

- Industrial	- Rs.100 per assessment

- Bio-medical 	- Collected by IMA.

- Privatisation/involvement of SHGs in collection, transfer, construction and management of compost yard and compost production. This would reduce the O&M expenses of Town Panchayat on SWM by 30 to 40%.

- Revenue generation from selling scrap after segregation at secondary collection point or compost yard at Rs.5 – Rs.10 per kg.

Revenue generation from the sale of compost at the rate of Rs.1000 per ton, as bulk supply to the nearby agricultural areas. Incidentally, the manure generated from garbage is found to be richer in NPK values compared to the one available in the market. This has resulted in producing better yield of agricultural products both in quantity and quality.

## Table 7.2 Road Map for Improving revenue from user charges

| S.N | Reforms |  | Year of Implementation |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| 1 | Water Supply and UGSS |  |  |  |  |  |  |
|  | i | Revision of deposit and tariff structure |  |  |  |  |  |
|  | ii | Fixing of bulk water meter |  |  |  |  |  |
|  | iii | Graded tariff for Sewerage system |  |  |  |  |  |
|  | iv | Pre mobilization of deposits |  |  |  |  |  |
| 2 | Solid Waste Management |  |  |  |  |  |  |
|  | i | Collection of conservancy fee |  |  |  |  |  |

      - Strategies for Formation of New Sustainable Revenue Bases

i.	Remunerative projects

To improve the revenue base of the Town Panchayat, following are the remunerative proposals identified within Town Panchayat area.

ii.		Parking Regularisation Plan

Enforcing no-parking zones and identification of possible parking areas with the involvement of stakeholders would be the first step in mitigating congestion in the central areas of the town. Preparation of inventory for all roadside parking area within the town. Initiating time based pay and park facilities for vehicles. Appropriate rent structure from light carriage vehicles and heavy vehicles parking would also improve income generation.

The proposed parking fee structure is:

  - Two wheelers	- Rs.2.00 per day

  - Light Vehicles	- Rs.5.00 per day

  - Heavy Vehicles	- Rs.10.00 per day

iii.	Advertisement Regularisation Plan

Identifying strategic locations such as bus shelters, road medians, for hoardings and poster places in Town Panchayat area and levying advertisement tax at the rate of Rs.500 per board per annum.

To prepare an inventory of advertisement spaces within their limits with size and type. Auctioning the entire rights to a single bidder on an annual basis is suggested. The initiative of GoTN to remove hoardings and encroachments is a welcome step to regularize the advertisements and hoardings.

iv.	Collection of Annual Tract rent

    - From cable T.V operators 			       -	Rs. 5000 per km

    - From Telecommunication service providers   -	Rs.5000 per km

The urban local body may be empowered to collect the security deposits at Rs.10,000 per operator and revise the tract rent every three years.

Table 7.3 Road Map for formation of new sustainable revenue bases

| S.N | Reforms |  | Year of Implementation |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| 1 | Formation of new sustainable revenue bases |  |  |  |  |  |  |
|  | i | Remunerative Projects |  |  |  |  |  |
|  | ii | Parking Regularization |  |  |  |  |  |
|  | iii | Advertisement Regularization |  |  |  |  |  |

## 7.3.2	Privatisation Initiatives

The areas of privatization of the functions of the ULB in Tamil Nadu are

- Solid Waste Management

- O&M of street lights.

- O&M of water supply distribution.

- AMC of public and pay & use toilet facilities.

- Parks and parking lots Maintenance and user charges collection.

The GoTN states that the above list is indicative and the ULBs are free to explore more options. This would not only save the O&M expenses, but also indirectly in pension and gratuities.  The various strategy options are presented below:

7.3.2.1	Strategies for Privatisation

- Privatizing Collection mechanism: Providing automated billing machine with online access to database for spot billing and collection of all taxes. Performance based incentives can be given to the private operators at the rate of  5% of total collection .The support of the Youth / Women SHGs or fan clubs can be sought for the purpose of collection with adequate sensitization programmes.

- Improving community participation by organizing Public awareness campaigns and Training of Tax Inspectors, to improve the ‘willingness to pay’ of the users. The aid of SHGs, fan clubs, media could be utilized for the purpose. The following are the various avenues of revenue, the collection of which could be privatized.

- Property tax

- Profession tax

- Water - Deposits and tariff

- UGSS- Deposits and tariff

- Advertisement spaces /rights as a single contract

- Parking areas

- Solid waste conservancy fees(Domestic and non-domestic)

- Privatisation of Operation and Maintenance of the entire Water Supply and Distribution System.

- Privatisation of operation and maintenance of the Sewerage system.

- Privatisation of Solid waste management (Discussed in detail under Improving revenue from user charges)

- Privatisation of O&M of street lights & pumping machinery(detailed out in Action plan for energy & resource efficiency)

- Repair and maintenance of major Town Panchayat roads for 3 years from the period of laying.

- Option of BOT, BOOT for parks & play grounds by implementing user charges for areas more than 10,000 sft.

- Option of converting public toilets to Pay & Use type and privatization of O&M.

- Private participation in medical infrastructure like RCHP, maternity homes and primary urban health centers (5 year plan policy) from the corporate sectors.

Table 7.4 Road Map for Privatization initiatives

| S.N | Reforms |  | Year of Implementation |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| 1 | Privatization of Operation and Maintenance |  |  |  |  |  |  |
|  | i | Water supply and Distribution system |  |  |  |  |  |
|  | ii | Sewer network & STP |  |  |  |  |  |
|  | iv | Street lights |  |  |  |  |  |
|  | vi | AMC of Public and Pay & Use toilet facilities |  |  |  |  |  |
|  | vii | Parks and parking lots Maintenance and user charges collections |  |  |  |  |  |
| 2 | Privatisation options in Solid Waste Management |  |  |  |  |  |  |
|  | Privatization of Door to door collection of solid waste |  |  |  |  |  |  |
|  | Compost yard Management & Sale of compost & scrap |  |  |  |  |  |  |
| 3 | Privatization of Collection mechanism |  |  |  |  |  |  |
|  | Spot billing and tax collection using automated billing machine |  |  |  |  |  |  |
| 4 | Formation and sensitisation of youth & Women SHGs |  |  |  |  |  |  |
| 5 | Public awareness campaign for improving tax collection (IEC) |  |  |  |  |  |  |

## Energy and Resource Efficiency

i.	Strategy for energy efficiency

  - Conducting energy audits for water pumping machinery and street lights.

  - Conducting leak detection studies, if transmission losses are more than 15%.

  - All Head works and service reservoirs may be fitted with bulk water meter to assess the loss due to non revenue water and unaccounted water.

  - Enforce regulations on illegal tapping of water.

  - Fixing Flow Control Valves and meters for all water service connections.

  - Provision of energy saving lights, and equipments like dimmer and timer switches to reduce energy consumption.

  - Privatizing the maintenance of street lights with ESCO companies.

Table 7.5 Road Map for Energy and Resource efficiency

| S.N | Reforms |  | Year of Implementation |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| 1 | Energy audit |  |  |  |  |  |  |
|  | i | Leak detection study |  |  |  |  |  |
|  | ii | Fixing of bulk water meter |  |  |  |  |  |
|  | iii | Fixing flow control values & meters |  |  |  |  |  |
|  | iv | Implementing energy saving measures on street lights and pumping machineries (ESCo) |  |  |  |  |  |

## 7.3.4	Computerization and E-Governance

Strategies for Computerization and E-Governance

- Launch data warehousing on a large scale, which would avoid cross-reference to paper record, which are time consuming and also preservation of paper media, which occupies space, could be avoided.

- Computerization of  bill payment and facilitation of  on line payments

- Computerisation of registration of land records within Town Panchayat limit

- Digitisation of Birth and death certificates for the past 30 years

- Property Mapping to be computerised and details on area, year of construction, type of assessment to be computerized to facilitate calculation of property tax.

- Administration and issue of trade licenses to be on line, including payment and reconciliation of license fee.

- Computerization of birth and death certificates and on line issue of certificates.

- Computerization of public grievances and Redressal mechanism

- Introduction of Asset Management System for all the available land and building assets available with the Town Panchayat

- On-line submission of building plans and approval.

- Track O&M of assets and their replacement

- E-tendering processes.

The above proposal can be taken up after giving sufficient training to ULB staff in hard ware and software.

Table 7.6 Road map for Computerization and E-Governance

| S.N | Reforms |  | Year of Implementation |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |
| 1 | Computerization and E-governance |  |  |  |  |  |  |
|  | i | Digitizing municipal records (past 30 yrs) |  |  |  |  |  |
|  | ii | On-line bill payment |  |  |  |  |  |
|  | iii | Registration of Land records |  |  |  |  |  |
|  | iv | Digitization of old Birth and death certificates |  |  |  |  |  |
|  | v | On-line issue of Birth and Death certificates |  |  |  |  |  |
|  | vi | Property Mapping |  |  |  |  |  |
|  | vii | on-line Issue of trade license |  |  |  |  |  |
|  | viii | Online submission of building plans |  |  |  |  |  |
|  | ix | E-tendering |  |  |  |  |  |

## 7.3.5	Accounts and Auditing

  - A Consultant committee of chartered accountants, consultants having experience in accounting ULB accounts should be constituted to provide training to the Town Panchayat employees.

  - Timely Auditing should be performed with the use of private Chartered Accountants for routine audit and local audit to carry out proprietary audit.

  - Closing all Auditing before September 30 of the next financial year and publishing the audited statement on the website.

## Table 7.7 Reform Agenda - Municipal Service Delivery

| Sector | Particulars | Benchmark considered | Existing | Target |  |  |  |  | Outcome After 5 years |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | Year 1 | Year 2 | Year 3 | Year 4 | Year 5 |  |
| WATER SUPPLY | Net Supply per capita | 70 lpcd | 40 lpcd | 70 | 100 | 135 lpcd (proposed to annex with Chennai corporation) |  |  |  |
|  | HSCs - % of assessed properties | ≥85% | Nil | 30% | 50% | 75% | ≥85% |  |  |
|  | Frequency of Supply - Hours per day | 24x7 hours | Daily | - |  |  | 24x7 |  |  |
| SEWERAGE SYSTEM | HSC coverage | ≥85% | Nil | - | Period of Implementation |  | ≥85% |  |  |
|  | Coverage of UGSS network - % of road length | 100% | Nil |  |  |  | 100% |  |  |
| SOLID WASTE MANAGEMENT | Availability of Composting facility | 100% available | Not in use | Period of Implementation |  |  | 100% available |  |  |
|  | Collection efficiency | 100% | 100% | 100% |  |  |  |  |  |
| ROADS, STORM WATER DRAIN, STREET LIGHTS | Surfaced roads - % of total road length | 100% | 98% | - | - | Period of Implementation |  | 100% |  |
|  | Storm water drains - % of total road length | 130% | 29% |  |  | Period of Implementation |  | 130% |  |
|  | Average spacing between Street lights | 30m | 40 m | Period of Implementation |  | 30m |  |  |  |

Source: Analysis and research

7.4	PRIORITY ASSET MANAGEMENT

All the assets developed, operated and maintained by the Town Panchayat are termed as Town Panchayat assets and comprise roads, bridges, culvert, water supply & distribution system, UGSS network, STPs, drains, and street lights. Town Panchayat Assets also includes social infrastructure assets such as parks and playgrounds, community halls, shopping complexes, and vacant lands.

Town Panchayat assets are normally classified into movable and immovable assets. Immovable assets attain importance as indicators for the financial worth which would help in its borrowing capacity and credit worthiness of Perungudi Town Panchayat.

The management of assets in the local bodies is at the initial stage where, only the assets are listed and status is described. Invariably, in all the cases, the management component is missing as to the techniques and methods of managing the assets either in improving their state and value or in sustaining them with a growth motive. There is hardly any case where a local body has made use of its immovable assets for raising loans or improving its borrowing capacity. It requires an overall approach outlining the alternative options of maintaining and managing the assets in a worthwhile mode.

The Asset Management Plan for Perungudi Town Panchayat would comprise the following 5 steps as explained below:

- Asset identification

All movable and immovable equipments, immovable municipal properties, assets of Town Panchayat that have been developed, handed over or acquired over time from various sources and departments have to be identified and traced. This would include the detection of unrecorded infrastructure facilities and properties; scrutiny of records, land registers and land surveys, etc.

- Audit and reconciliation of records

The Town Panchayat should record all movable and immovable municipal properties and assets and infrastructure facilities. Maps and master plans should be crosschecked and an infrastructure facilities audit should be prepared or updated (if already existing). Current asset values should be assigned based on a ‘condition-survey’ of the infrastructure facilities.

Land and property records should be crosschecked and Town Panchayat registers to be updated to include previously undetected land, properties and development. A comprehensive list of Town Panchayat owned land, properties and development should be compiled with approximate assigned.

- Assessment of Remunerative potential

Town Panchayat should review the existing revenue earning potential of all its assets. New projects or initiatives should be taken to maximize the revenue earning potential of assets including infrastructure facilities. The intangible benefits of social facilities also need to be considered in the process.

- Digitisation of asset register

Focus should be placed on designing, testing and installing a database management system for Town Panchayat assets. All data, once complied should be classified on the basis of sector specific infrastructure facilities, land and properties. Specific software should be customized to suit local requirements and data should be translated into specified formats.

- Training in database management

Training is the most important part of an asset management plan. Training should emphasize methods of simplified updation of data, and methods of monitoring and follow-up relating to infrastructure facilities management, land use, litigation, encroachment, values, expenditure and revenue flows.

7.4.1	LAND ASSETS

The land varies in its value from location to location and time to time as per the weightage of the area arrived at based on various factors. It is invariably found that, the value of the ULB land varies substantially from that of the adjacent private land for obvious reasons. These differences need a practical moderation to estimate the true credit worthiness of the local body.

The rate of increase of the ULB land in its value, vis-à-vis that of the adjacent private land at the various locations will be useful in drawing up a reasonable assets management technique.  The existing land asset and building asset details are given in Annexure 3.

7.4.2	MANAGEMENT OPTIONS FOR LAND ASSETS

The foregoing account of the movable and immovable assets of the Town Panchayat includes basically lands, parts of which are occupied by construction of structures for various uses. The structural elements in the form of buildings including OHTs, flow elements relating to essential services such as water supply, drainage, UGD, street lights and the like are designed with a design life time. The lands however as a base have no such limiting factor in terms of time. Thus the super structures and the constructed elements below the ground are depreciating in their values as they age. But the land assets both constructed and un-constructed keep appreciating in the standard and market values. In fact, the rate of appreciation of the lands is of great significance from the point of worthiness of the concerned local body and, it is invariably much faster in its appreciating value compared to the rate of depreciation of structures imposed on them. Also, the rate of depreciation standardized for various items of the structures is much more than the actual while taking into consideration the life time of such structures till the point of their condemnation.

Generally, the assets of the local body, particularly the lands are rarely maintained and their values in the management of the resources of the local body are little considered. There must be a scientific approach town wise to evolve a dynamic model of the changing values of the assets both in terms of appreciation and depreciation from time to time, particularly when sizable developments take place. It is important to keep in view that as per the objectives of the devolution of functions and powers to the urban local bodies under the 74th Constitutional Amendment Act, the value of the lands and properties are necessarily to be assessed depending on their location, land use and intensity of development over a time scale. In order to systemize the highly dynamic factor of values of the properties under local body, it is essential for an efficient management of the total assets owned by local body.

The suggestions for the improvement of land asset management are listed below:

- Implementation of Asset Management Plan

- Establishment of GIS inventory mapping for Town Panchayat owned lands.

- Use of land assets for borrowing loans from capital market.

- Identifying the most remunerative activity by public–private participation, BOT, BOOT initiatives.

- Removal of encroachments on Town Panchayat land parcels.

- Explore possibilities of acquiring additional land parcels for future requirements

7.5	TECHNICAL ASSISTANCE:

Technical assistance and Capacity building of ULB Officials and Elected Representatives is essential to sustain the proposed reforms, which in turn support the effective implementation of the Capital Investment Plan. The objective of the technical assistance is to strengthen institutional capabilities, and improve overall readiness for project implementation.

The categorization of technical assistance is based upon the position at various levels focusing on managerial aspects, application of reforms for physical, socio-economic and fiscal development, technical knowledge related to formulation and implementation of priority projects, skills, management tasks and awareness about responsibilities. State government may organize suitable training as well as capacity building programmes through reputed institutions in the fields.

7.5.1	CAPACITY BUILDING FOR ELECTED REPRESENTATIVES

The details of the various training requirements for elected representatives and Committee members are presented below.

Table 7.8 Technical Assistance for Elected representatives

| Category | Identified Training areas |
| --- | --- |
| Elected representatives | - Visioning, goal setting, Planning - Urban Governance, Management and Planning - Social management and Management of Urban Poor - Financial and cost management - Budget preparation - Tender procedure - Training in interpretation of various laws, rules, regulations and statutes that ULB is bound by - E - Governance - Redressal of public grievances - Environment management - JNNURM, UIDSSMT, IHSDP & BSUP - Town Investment Plans , Urban Development plans (Master plans, DDPs) - Solid waste management. - Disaster management - Managerial development and effectiveness - Public relations and Human resource development. - Crisis management and Stress management - Personality development and Motivation skill development - Written and Oral Communication skills |

## 7.5.2	CAPACITY BUILDING FOR ULB STAFF

The training areas identified for ULB staff in all position is classified as functional, managerial & behavior and attitude in short, medium and long term training. The details of the various training requirements for ULB staff are presented below.

Table 7.9 Technical Assistance for ULB staff

| Category | Identified Training areas |
| --- | --- |
| Senior Management Staff | - People management skills - Motivation and Interpersonal skills - Leadership and Public relations - Attitudes – both personal and organizational - Team Building, Human resource development - Goal setting, Budgeting - Written and Oral Communication skills - Effective use of computers especially for managerial decision making - Proper interpretation and effective use of MIS reports - Decision support systems - Training in interpretation of various laws, rules, regulations and statutes - Time management, Stress management - Change management - Effective urban management - Management principles, Managerial development and effectiveness - Interviewing skills - Social management and urban poor management - Citizen grievance handling - Project appraisal, Project Management and project financing - Contract management, Bid management, Costing - Procurement procedures - Pricing and tariffs/taxation methodologies - Operations research - Quality control - Public private partnerships and opportunities for ULB in the same - Reforms at the ULB level - Financial and cost management - Environment management - Disaster management - Solid waste management - Systems management (improving citizen service and ULB efficiency) - Strategic urban planning - Performance management system and key result areas. |
| Supervisory Staff | - Motivation and Interpersonal skill development - Effective use of computers - Training in interpretation of various laws, rules, regulations and statutes - Training for development of a positive attitude - Citizen handling and grievance handling - Managing urban poor, education and health services - Implementation skills - Training in developing a Performance Management Systems (PMS) and key Result Areas (KRA) |
| Training for Operational staff | - Functional skills required in their respective function - Training in office Procedures - Training in computers - Training in team work - Training in general office administration and management - Training in effective servicing - Training in communication - Training in equipment usage |

Source: CMA Records.