ANNEXURE-1

MINUTES OF MEETING

Minutes of meeting for review of Inception Report submitted by M/s. Fichtner Consulting Engineers India Pvt.Ltd for City Investment Plan (CIP) for Gandhi Nagar, Chengam, Polur, Allapuram, Kottakuppam, Sembakkam, Sozhanganallur and Perungudi Town Panchayats (Cluster 2) held on 27.08.2009 at 3.00 PM at TNUIFSL office.

List of Participants:

- Mr.P.Mohanarangan, EO, Perungudi

- Mr.M.Venkatesh, EO, Sembakkam

- Mr.N.Ameenur Rahman, AEE, ADTP, Vellore

- Mr.G.Ravichandran, Jr.Asst, Allapuram

- Mr.G.Elanparithi, EO, Gandhinagar

- Mr.M.J.Sampath, EO, Sozhanganallur

- Mr.N.Sekar, AEE, T.V.Salai

- Mr.C.Mathivanan, EO, Chengam

- Mr.V.Sulaiman Sait, EO, Kottakuppam

- Mr.D.Rajendiran, AVP, TNUIFSL

- Mr.M.Sudharshan, Manager, TNUIFSL

- Mr.U.Vijayaraghavanm, DM,TNUIFSL

- Ms.V.Priya ,Urban Planner, Quadra Architects

- Mr.S.Abdul Gafoor ,Town Planner, Quadra Architects

- Mr.S.Ashmy, Urban Planner, Quadra Architects

- Mr.P.Sudharsanamurthy, Urban Planner, Quadra Architects

- Mr.S.Sriram, Finance Consultant, Fichtner

- Mr.E.N.Narayanan, Chief Engineer, Fichtner

The consultants submitted the inception report and made presentation on the City Investment Plan (CIP) for Gandhi Nagar, Chengam, Polur, Allapuram, Kottakuppam, Sembakkam, Sozhanganallur and Perungudi Town Panchayats (Cluster 2) in detail and the consultants were requested to

1. To conduct stakeholders’ consultations to ascertain the demands from public to identify infrastructure gaps.

2. To present the draft final report to respective ULBs in the council after incorporating the suggestions of stake holders meeting.

3. Study on the unused / underutilized assets of the ULB and suggest ways for the better utilization of the same.

4. To identify any vacant land for commercial development.

PERUNGUDI:

- Necessary correction to be made in SWOT analysis.

SOZHANGANALLUR:

- To update / revise the data on population

- The project cost for UGSS should be in accordance to the DPR.

KOTTAKUPPAM:

To revise / update:

- The cost of land fill site in consultation with ULB.

- The data on SWM workers

- The cost of Social Infrastructure

POLUR:

- Water Supply project cost to be rechecked.

- Bus shelters to be included in consultation with ULB

CHENGAM:

- Water Treatment plant cost to be included in Water Supply project, since the present water available is not potable.

- Water body improvement to be addressed.

The representatives of ULBs were requested to provide details of all the assets to the consultants and the consultants were requested to include the same and suggest optimum utilization of the assets. The inception report submitted by the consultant is approved and consultant was requested to incorporate the above comments in draft final report and adhere to the schedule as per the Term of Reference for submitting the Draft Final Report.